## Dashboard
AI Cost Management Strategy — First 90 Days
Progress tracker for standing up an enterprise AI cost program
Phase | Window | Theme | Total Tasks | Done | In Progress | Not Started | Blocked | % Complete
Phase 1 | Days 1–30 | Visibility & Baseline | 12 | 0 | 0 | 12 | 0 | 0%
Phase 2 | Days 31–60 | Gateway, Governance, Showback | 11 | 0 | 0 | 11 | 0 | 0%
Phase 3 | Days 61–90 | Operating Model & Optimization | 12 | 0 | 0 | 12 | 0 | 0%
Total | Days 1–90 | All phases | 35 | 0 | 0 | 35 | 0 | 0%
By Pillar
Pillar | Total Tasks | Done | % Complete
1. Visibility & Unit Economics | 5 | 0 | 0%
2. Architecture & Model Economics | 5 | 0 | 0%
3. Governance & Guardrails | 10 | 0 | 0%
4. FinOps Operating Model | 11 | 0 | 0%
5. Continuous Optimization | 4 | 0 | 0%

## 90-Day Plan
# | Week | Phase | Pillar | Task | Deliverable / Definition of Done | Suggested Owner | Priority | Status | Target Date | Notes
1 | W1 | Phase 1 | 1. Visibility & Unit Economics | Identify the anchor workload to instrument first | One named production workload selected; written rationale (volume, cost, business visibility). | Program Lead | P0 | Not Started
2 | W1 | Phase 1 | 3. Governance & Guardrails | Confirm executive sponsor and steering committee | Sponsor named; steering cadence on calendar; charter draft circulated. | Program Lead | P0 | Not Started
3 | W1 | Phase 1 | 1. Visibility & Unit Economics | Shadow-AI sweep: inventory all AI use cases and vendors in flight | Single register listing use case, owner, vendor, data sensitivity, monthly spend (if known). | FinOps + Security | P0 | Not Started
4 | W2 | Phase 1 | 1. Visibility & Unit Economics | Define the tagging schema for AI calls | Schema documented: business unit, product, feature, environment, user cohort, business-event ID. | Platform Lead | P0 | Not Started
5 | W2 | Phase 1 | 1. Visibility & Unit Economics | Stand up basic telemetry on the anchor workload | Per-call log captures tokens in/out, latency, model, prompt size, tags. Stored in queryable system. | Platform Eng | P0 | Not Started
6 | W2 | Phase 1 | 4. FinOps Operating Model | Establish 90-day baseline cost | Baseline monthly AI run-rate documented; broken down by BU and use case where possible. | FinOps | P0 | Not Started
7 | W3 | Phase 1 | 1. Visibility & Unit Economics | Define unit economics for the anchor workload | Cost-per-outcome metric defined and computed (e.g., $ per resolved ticket, $ per generated report). | Program Lead + BU Owner | P0 | Not Started
8 | W3 | Phase 1 | 2. Architecture & Model Economics | Prompt-hygiene audit on top 3 workloads | Audit findings with sized opportunities (verbose system prompts, missing max-tokens, history bloat). | AI Eng | P1 | Not Started
9 | W3 | Phase 1 | 4. FinOps Operating Model | Inventory current model vendor contracts and negotiated rates | Contract register: vendor, term, committed spend, list vs. effective rate, renewal date. | Procurement | P1 | Not Started
10 | W4 | Phase 1 | 2. Architecture & Model Economics | Quick-win pass: max-tokens, streaming cancel, history truncation on anchor workload | Implementation merged; measured impact on cost-per-outcome reported. | AI Eng | P1 | Not Started
11 | W4 | Phase 1 | 4. FinOps Operating Model | Stakeholder map of BUs running AI | Map of BUs, accountable owners, current spend, and willingness-to-engage rating. | Program Lead | P1 | Not Started
12 | W4 | Phase 1 | 3. Governance & Guardrails | Draft model-access policy (who can call what, from where) | Draft policy circulated to security, legal, and BU leads for comment. | Security + Program Lead | P1 | Not Started
13 | W5 | Phase 2 | 3. Governance & Guardrails | AI gateway build-vs.-buy decision | Decision memo: selected approach, cost, timeline, exit criteria. | Platform Lead | P0 | Not Started
14 | W5 | Phase 2 | 3. Governance & Guardrails | Implement gateway in front of the anchor workload | Gateway routing 100% of anchor-workload traffic; tagging enforced; logs flowing to telemetry. | Platform Eng | P0 | Not Started
15 | W6 | Phase 2 | 2. Architecture & Model Economics | Roll out semantic cache on high-traffic patterns | Cache deployed; cache-hit-rate dashboard live; observed savings reported weekly. | AI Eng | P0 | Not Started
16 | W6 | Phase 2 | 3. Governance & Guardrails | Implement policy-as-code at the gateway | Model-access policy enforced programmatically; violations logged and alerted. | Platform Eng + Security | P0 | Not Started
17 | W6 | Phase 2 | 3. Governance & Guardrails | Approval workflow for new use cases above a cost threshold | Intake form, threshold defined, approver list, SLA — all live. | Program Lead | P1 | Not Started
18 | W7 | Phase 2 | 3. Governance & Guardrails | Baseline guardrails: PII redaction, output filtering, data-residency checks | Guardrail policies deployed at gateway; test cases pass; exceptions documented. | Security + Platform Eng | P0 | Not Started
19 | W7 | Phase 2 | 3. Governance & Guardrails | Quota and rate-limit policies per BU / product | Policies defined and enforced at the gateway; breach alerts wired to FinOps. | Platform Eng | P1 | Not Started
20 | W7 | Phase 2 | 5. Continuous Optimization | Stand up evaluation harness for the anchor workload | Repeatable eval suite with quality bar defined; CI integration where possible. | AI Eng + QA | P0 | Not Started
21 | W8 | Phase 2 | 2. Architecture & Model Economics | Pilot tiered routing on the anchor workload | Small-model-first with escalation live; A/B vs. baseline shows cost reduction with no eval regression. | AI Eng | P0 | Not Started
22 | W8 | Phase 2 | 4. FinOps Operating Model | Build first showback dashboard | Per-BU monthly view of spend + unit economics; reviewed in first monthly forum. | FinOps | P0 | Not Started
23 | W8 | Phase 2 | 4. FinOps Operating Model | First monthly AI cost review with BU leads | Meeting held; minutes circulated; 3 commitments captured per BU. | Program Lead | P1 | Not Started
24 | W9 | Phase 3 | 3. Governance & Guardrails | Onboard 2 additional workloads behind the gateway | Two new workloads cut over; tagging and guardrails verified; baselines captured. | Platform Eng | P0 | Not Started
25 | W9 | Phase 3 | 4. FinOps Operating Model | Roll out showback to all participating BUs | All BUs receive monthly statements; questions logged and resolved within SLA. | FinOps | P0 | Not Started
26 | W9 | Phase 3 | 4. FinOps Operating Model | Establish forecasting cadence with FP&A | Monthly forecast process documented; first forecast delivered with confidence bands. | FinOps + FP&A | P1 | Not Started
27 | W10 | Phase 3 | 4. FinOps Operating Model | Renegotiate vendor terms using consolidated leverage | At least one renegotiated agreement; documented effective-rate improvement. | Procurement | P1 | Not Started
28 | W10 | Phase 3 | 4. FinOps Operating Model | Budget alerting thresholds per BU and per workload | Thresholds configured at 50/75/90/100% with named recipients; first alert tested. | FinOps + Platform Eng | P1 | Not Started
29 | W10 | Phase 3 | 4. FinOps Operating Model | Define chargeback policy effective in Q+1 | Policy approved by Finance and steering committee; communication plan ready. | Finance + Program Lead | P1 | Not Started
30 | W11 | Phase 3 | 5. Continuous Optimization | Stand up monthly optimization review cadence | Recurring meeting on calendar; standing agenda covering model mix, cache hit, prompt hygiene, eval drift. | Program Lead | P1 | Not Started
31 | W11 | Phase 3 | 5. Continuous Optimization | Run first formal eval regression after cost optimizations | Eval results documented; no statistically significant quality regression on anchor workload. | AI Eng + QA | P0 | Not Started
32 | W11 | Phase 3 | 5. Continuous Optimization | Define program KPIs and publish baselines | KPI sheet: $/outcome, cache hit rate, model mix %, eval pass rate, % traffic via gateway. | Program Lead | P1 | Not Started
33 | W12 | Phase 3 | 4. FinOps Operating Model | Quarterly business review with AI spend on agenda | QBR held; AI spend reviewed alongside revenue and gross margin; next-quarter commitments set. | CFO Office + Program Lead | P0 | Not Started
34 | W12 | Phase 3 | 3. Governance & Guardrails | Publish the AI cost playbook | Playbook covering tagging, gateway use, model selection, eval, intake. Stored in central knowledge base. | Program Lead | P1 | Not Started
35 | W12 | Phase 3 | 2. Architecture & Model Economics | Identify next-wave workloads for the gateway and routing | Prioritized backlog of 5+ workloads with sized opportunity. | Program Lead + Platform Lead | P2 | Not Started

## Legend
How to use this workbook
This is a tactical checklist for the first 90 days of standing up an AI cost management program.
Work through the 90-Day Plan tab; the Dashboard rolls up progress automatically.
Tasks are mapped to the five-pillar framework: Visibility, Architecture, Governance, FinOps, Optimization.
Priority
P0 | Must-have. Program credibility depends on this being done on time.
P1 | Important. Plan to complete in window; can slip a week if forced to triage.
P2 | Helpful. Do if capacity allows; otherwise push to days 91–120.
Status
Not Started | Default state for all new tasks.
In Progress | Actively being worked; owner is engaged this week.
Done | Definition of done met and verified; deliverable in place.
Blocked | Cannot progress without external input; escalate at next steering review.
The Five Pillars
1. Visibility & Unit Economics | Tagging, telemetry, cost-per-outcome — make AI spend legible.
2. Architecture & Model Economics | Routing, caching, RAG vs. fine-tune, build vs. buy.
3. Governance & Guardrails | Policy-as-code, access controls, AI gateway, approval workflow.
4. FinOps Operating Model | Ownership, showback/chargeback, forecasting, budgets, procurement.
5. Continuous Optimization | Monthly review cadence, eval regression, prompt hygiene, model refresh.